## Group member 4
To-do list Project 3
To be completed by: |  | ESFAR(PROJ MANAGER)11/30/2025 |  | Names: Esfar, Justin, Sayantan, Fahim, Yousuf
Deadline: |  | 2025-11-30 |  | Date: 11/30/2025
Chapter 4 and 5
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | Group meets to review instructions, confirm deliverables, and assign roles.
95% | Step 1 – Data Cleaning (All Data. Tables)* | 2025-11-22 | 2025-11-23 | 2025-11-23 |  | Cleaned Data.Country, Data.Make, Data.Model, Data.Stock, and verified no bad data.
90% | Step 2a – Add Primary Keys | 2025-11-23 | 2025-11-24 | 2025-11-24 |  | Members helping each other to add all PKs after validating rows.
90% | Step 2b – Add Unique Constraints | 2025-11-24 | 2025-11-25 | 2025-11-25 |  | Added UNIQUE on key business columns (CountryName, MakeName, SalesID, Pivot.Color)
90% | Step 2c – Add Check Constraints | 2025-11-25 | 2025-11-25 | 2025-11-26 |  | Added CHECKs for ISO lengths, price floors, discount floors, RHD flag values, invoice format.
95% | Step 2d – Add Foreign Keys | 2025-11-25 | 11/25+Project16711[@[Original Due By2]:[Revised Due By]]/2025 | 2025-11-26 |  | Enforced FK links between Make ← Model, Model ← Stock, Sales ← Customer, SalesDetails ← Sales + Stock.
85% | Step 3 – Normalization (2 tables) | 2025-11-27 | 2025-11-27 | 2025-10-27 |  | Normalized Model (3NF). Prepared before/after diagrams.
80% | Step 4 – Create UDTs & Apply FQDN | 2025-11-27 | 2025-11-28 | 2025-11-28 |  | Created UDTs; Esfar applied them; Justin converted queries to full FQDN format.
95% | Step 5 – Final Script Compilation | 2025-11-28 | 2025-11-29 | 2025-11-30 |  | Group merged all scripts, tested PK/FK/unique/check constraints, and validated data integrity.
93% | Step 6 – Group Presentation & Recording | 2025-11-30 | 2025-11-30 | 2025-10-10 |  | Recorded walkthrough explaining cleaning, constraints, normalization, diagrams, and final DB design.